## System Dev. Plan
SYSTEM REQUEST FORM
(New System Introduction / System Enhancement / Bug Fix)
System Development Plan
System : |  |  | Gprism
Module :
Subject : |  |  | PS00S01002490 - Picture Perusal Track Out
Please indicate 'Y' (Yes) or 'NA' (Non-Applicable) in the BOX for the maintenance of the documents of the following items. MANDATORY. If 'Y', please attach its related documents or indicate the reference document.
System Outline
[5 empty] | Document Maintained (if others, please specify) | Explantion Note
| (1) | Request Background / Description |  | Y | System Request Form | Management issues / User division request
| (2) | Aims of System Construction |  | Y | System Request Form | Objectives / Benefits
| (3) | Outline of IT Solutions |  | Y | System Request Form | Solution Details
| (4) | Business Flow |  | NA | Blueprint | Business Flow Diagram, Process Flow Diagram
| (5) | Diagram of System Outline |  | Y | Functional Specifications | User divisions, functions and outline of information
FS Version No. :
| (6) | Outline of Functions |  | Y | Functional Specifications | Explanation of functions
| (7) | Outline of Input & Output |  | Y | Functional Specifications | List of major screens and reports
`
| (8) | System Interface |  | N | Functional Specifications | Method to send/receive data
| (9) | Testing |  | Y | Test Plan and Test Result | Test Plan defind the scope of test & test scenarios
Test result register the result of the test scenarios
| (10) | Migration Plan |  | N | Common Contingency Plan | Outline of migration method, estimated period and scale
as in Procedure for
System development / Major System Enhancement
(For CIM system - fill "CIM System - Program Migration Check List)
Promotion Schedule |  |  |  | Y | System Request Form / Project DCP Meeting | Schedule of all processses in this project
Project Structure
| (1) | Organization Chart for Basic Design |  | NA | Project DCP Materials | Organization chart (members), roles, responsibilities and authorities
| (2) | Project Management |  | NA | Project DCP Materials | Purpose of meetings, frequency of meetings, participants
| (3) | Total Man-Days |  | Y | System Request Form / Project DCP Materials | Total system development effort
1
Cost Effectiveness
| (1) | Cost |  | NA | Project Investment Plan | Estimated development cost and operation cost
| (2) | Effect / Benefit |  | NA | Project Investment Plan | Quantitative and qualitative effect / benefit
| (3) | ROI |  | NA | Project Investment Plan | Return on Investment
Management
| (1) | Information Security |  | Y | ISM | Classification of information, limit of disclosure, access control method, etc
For New System Introduction, Development that involves change in basic program design, Development that takes more than 10 man-days
and/or Critical program changes :
System devlopment plan is to be discussed and signed-off by Business Manager
Approved by (Business Manager)
(Name, Signature, Date) | [6 empty] | FMSC-MIS-001-13 G.REV1
INTERNAL USE ONLY
Access: PSCSG Project Members Only
INTERNAL USE ONLY
Access: PSCSG Project Members Only
INTERNAL USE ONLY
Access: PSCSG Project Members Only
INTERNAL USE ONLY
Access: PSCSG Project Members Only
INTERNAL USE ONLY
Access: Project Members Only

## Test Plan Signoff
PS00S01002490 - Picture Perusal Track Out
Test Plan Signoff Form
Request Title: |  | Gprism
Description : |  | The document summarises the Test plan and the Test Scenarios for program
No | Description
1 | Program Description
Ver | System Request Number | Purpose | Scope | System To Be Tested In | IT Dept. Schedule | To Be Tested By IT | User Dept. Schedule | To Be Tested /Acknowldged By | Approved by IT Dept. | Approved by User Dept.
[9 empty] | (Name, Sign.,Date) | (Name, Sign.,Date)
1 | Picture Perusal Track Out CCD Project | Picture Perusal Track Out | Test All Function | Gprism - DEV | 2017-04-18 | Mydel
Project Information
Company: |  | PIDSCSA
Project Name: |  | Machine Downtime Email Master
Note:
Only need to print the Test Plan Version corresponding to the System Request Number that is being serviced. (Use "hide" function.)
INTERNAL USE ONLY
Access: Gprism Project Members Only

## Test Plan
PS00S01002490 - Picture Perusal Track Out
Test Plan
Sub module | Sys Req No | Test ID | Test Scenarios | Option | Test Schedule | Expected Result | Actual Result | User Test (Name, Signature,Date) | IT Verification (Name, Signature,Date) | Status of Testing
|  | 1 | Scenario 1 : Check Allowed E9 [E921S021 - (CCD) PICTURE PERUSAL TEST] |  |  | 'If E9 is not same, show error message | Same as Expected result. | Mydel/2017-04-18 |  | OK
|  | 2 | Scenario 2 : Load all the values to the screen. |  |  | Display all the values to the screen. | Same as Expected result. | Mydel/2017-04-18 |  | OK
|  | 3 | Scenario 3 : Check required input |  |  | Error message shown if required inputs are empty | Same as Expected result. | Mydel/2017-04-18 |  | OK
|  | 4 | Scenario 4 : Check for illegal characters |  |  | Error message shown when inputs have invalid characters | Same as Expected result. | Mydel/2017-04-18 |  | OK
|  | 5 | Scenario 5 : Get the Picture Perusal Track-Out Information then Compare the user input and system track-out information |  |  | If input are not same with track-out, show error message | Same as Expected result. | Mydel/2017-04-18 |  | OK
|  | 6 | Scenario 6 : Update program details |  |  | Show a success message | Same as Expected result. | Mydel/2017-04-18 |  | OK
7
8
9
10
11
12
13
14
15
INTERNAL USE ONLY
Access: Gprism Project Members Only

## Scenario 1
Scenario 1 : Check Allowed E9 [E921S021 - (CCD) PICTURE PERUSAL TEST]
Expected Result | Actual Result
'If E9 is not same, show error message | Same as Expected result.
Invalid Lot ID

## Scenario 2
Scenario 2 : Load all the values to the screen.
Expected Result | Actual Result
Display all the values to the screen. | Same as Expected result.
For valid Lot ID display the values to the screen

## Scenario3
Scenario 3 : Check required input
Expected Result | Actual Result
Error message shown if required inputs are empty | Same as Expected result.
Empty Equipment Code
Empty Good Quantity
Empty Reject Quantity

## Scenario 4
Scenario 4 : Check for illegal characters
Expected Result | Actual Result
Error message shown when inputs have invalid characters | Same as Expected result.
Invalid characters on Equipment Code
Invalid characters on Good Quantity
Invalid characters on Reject Quantity

## Scenario 5
Scenario 5 : Get the Picture Perusal Track-Out Information then Compare the user input and system track-out information
Expected Result | Actual Result
If input are not same with track-out, show error message | Same as Expected result.
Input not match
Input matched

## Scenario 6
Scenario 6 : Update program details
Expected Result | Actual Result
Show a success message | Same as Expected result.
Update successfully